# Phased Implementation Roadmap

Governing thought: Each phase has a single governing question it must answer before the next begins: Phase 1 asks 'does the rail work and can we onboard merchants at all,' Phase 2 asks 'does it scale profitably,' Phase 3 asks 'does it compound into an ecosystem.' Moving to the next phase without a clean answer to the current one is the most common way roadmaps like this fail in execution, not in planning.

This roadmap operationalizes the Three Horizons framework (Section 4) into a phase structure aligned to board governance cadence — 6-month, 18-month, and 36-month review gates rather than continuous quarterly re-litigation of strategy.

## Phase 1 (0–6 months): Prove the Rail

Objective: establish that NEO PSP can onboard merchants, process transactions reliably, and operate within Bangladesh Bank's compliance framework — before committing capital to scale. This is a controlled launch, not a market-wide push.

|  | Details |
| --- | --- |
| Objectives | - Achieve commercial launch approval from Bangladesh Bank following NOC - Stand up core rail: transfers, bill pay, merchant QR acceptance via Mukto Pay/Huawei platform - Onboard first wave of merchants through Banglalink's existing enterprise relationships |
| Key initiatives | - Complete Huawei platform integration and institutional-grade reliability testing - Settlement bank partnership agreements finalized - Bangla QR interoperability compliance certification - First-wave SME merchant onboarding (warm-lead channel only) - SIM-linked customer onboarding flow live in Banglalink app/USSD |
| Dependencies | - Bangladesh Bank final commercial launch approval (beyond NOC) - Huawei platform delivery on committed timeline - Settlement bank agreements executed - Internal Banglalink enterprise sales team alignment on cross-sell mandate |
| Success metrics | - Commercial launch achieved within phase window - First 150–300 active merchants onboarded (illustrative target, see Financial Model) - Settlement reliability ≥99% from day one - Zero critical compliance findings from Bangladesh Bank |
| Major risks | - Regulatory approval delay beyond NOC — highest-probability, highest-impact risk this phase - Platform delivery slippage from Huawei integration complexity - Merchant onboarding slower than warm-lead assumption if Banglalink's B2B sales team isn't incentivized to prioritize it |
| Expected outcomes | - A working, compliant, reliable core rail with a small but real transacting merchant and customer base - Proof points to justify Phase 2 capital commitment — not yet a scale business |

## Phase 2 (6–18 months): Scale the Network

Objective: convert the proven rail into a genuine merchant network and open the SME/enterprise disbursement line — the differentiated white-space opportunity identified in the Competitive Benchmarking. This phase absorbs the bulk of Horizon 1–2 capital intensity.

|  | Details |
| --- | --- |
| Objectives | - Scale merchant acquisition beyond the warm-lead channel into underserved regions - Launch B2B disbursement product line (payroll, vendor payments) - Establish telecom–payments bundled propositions and unified loyalty construct |
| Key initiatives | - Agent-assisted merchant onboarding in underserved regions (Feni, Cumilla, Chattogram first; Panchagarh, Kurigram inclusion-focused expansion) - SME payroll/vendor disbursement product build and enterprise sales motion - Unified Banglalink–NEO PSP loyalty program launch - E-commerce/platform gateway partnership integrations - Merchant-side data personalization (settlement timing, fee-tier optimization) |
| Dependencies | - Phase 1 reliability and compliance track record clean enough to support scale-up - Dedicated headcount build in merchant acquisition, risk/compliance, and product (per Operating Model, Section 8) - Banglalink core telecom product team coordination on bundled propositions — flagged as a cross-functional risk earlier in this engagement |
| Success metrics | - Active merchant base scaling toward Year 2 target trajectory (see KPI Dashboard, Financial Model) - B2B disbursement revenue share reaching a meaningful proportion of total revenue (target: material double-digit share by end of phase) - Merchant retention rate sustained ≥95% - Cost per active merchant acquired trending down as warm-lead channel saturates and agent-assisted channel matures |
| Major risks | - Incumbent response — bKash/Nagad extending defensively into merchant/gateway services during this window - Execution risk in agent-network build-out, a capability Banglalink has not previously operated at this intensity - Telecom–payments bundling stalls if core telecom product team isn't formally resourced into the roadmap |
| Expected outcomes | - NEO PSP becomes a visible, scaling second growth engine rather than a pilot - B2B disbursement establishes NEO PSP's differentiated position ahead of any competitor closing the gap |

## Phase 3 (18–36 months): Compound the Ecosystem

Objective: move from a scaling payments business to a defensible financial-services ecosystem — layering adjacent services, consumer-side personalization, and open banking participation onto a now-established merchant and customer base.

|  | Details |
| --- | --- |
| Objectives | - Launch adjacent financial services (micro-savings placement, insurance premium collection) without carrying product risk directly - Participate in open banking/PISP ecosystem as the Bangladesh Bank framework matures - Establish NEO PSP as a replicable playbook for VEON's other operating markets |
| Key initiatives | - Consumer-side data personalization combining transaction and telecom usage data - Credit-referral data monetization partnerships with banks/NBFIs - Open banking/PISP participation (account-to-account payment initiation) - Third-party insurance/micro-savings distribution partnerships - VEON cross-market playbook documentation and knowledge transfer |
| Dependencies | - Bangladesh Bank open banking/PISP framework reaching sufficient maturity (targeted mid-2026, subject to regulatory pacing) - Sufficient transaction data volume and consent architecture from Phase 1–2 to support personalization reliably - Partner bank/NBFI agreements for credit-referral and product-distribution lines |
| Success metrics | - Revenue diversification: adjacent/ecosystem revenue lines contributing a growing non-MDR share of total revenue - EBITDA breakeven achieved or clearly in sight (see Financial Model breakeven flag) - At least one VEON cross-market replication conversation formally initiated |
| Major risks | - Open banking timeline slips, delaying the PISP-dependent revenue line — mitigated by treating this as upside, not core-case, per the Growth Framework's prioritization matrix - Over-expansion into adjacent services ahead of core profitability, repeating the capital-discipline risk flagged in the Executive Summary - E-commerce-native PSP entrants (Daraz, Chaldal) maturing into direct competitors for the same ecosystem plays |
| Expected outcomes | - NEO PSP operates as a diversified, increasingly self-funding digital financial services platform - A credible, documented case for VEON to evaluate replication in other operating markets |

## Cross-Phase Governance

- Each phase concludes with a formal steering committee gate review against the success metrics above — not an automatic progression.

- Phase transitions should be capital-gated: Phase 2 funding is not released until Phase 1's compliance and reliability metrics are clean; Phase 3 ecosystem investment is not released until Phase 2's B2B disbursement and merchant retention targets are met.

- This roadmap should be read alongside Section 9 (Risk Assessment) and the KPI Dashboard, which operationalizes the success metrics listed above into an ongoing tracking tool rather than a one-time checklist.